## NTT IPA Advisor Report
NTT Intelligent Pricing Application Advisor Report
General Information
|  | IPA Number |  | IPA13327
|  | Rate Card |  | USD TS/CS FY2020
|  | Client Name |  | ABM
|  | Deal Name |  | LAWA/LAX Smart Parking 072721
|  | Deal Type |  | Technical Service - Fixed Price
SFDC Number
Deal Version
|  | Deal Version Notes |  | Updating payment milestones
|  | Deal Currency |  | USD
Description
Notes
|  | Stage |  | Current Deals
|  | Creator |  | Michael Phillips
|  | Created |  | 7/27/2021, 10:49:49 AM
|  | Updated |  | 7/27/2021, 10:50:13 AM
|  | IPA Release Version |  | 20210716.1
| Service Name |  |  | Service Catalog |  | Activity/Task
| Network - LAN |  |  | Network - LAN |  | 5/16
| Security 4. Firewall/UTM Deployment |  |  | Security 4. Firewall/UTM Deployment |  | 6/30
Validations
|  | Margin |  |  | Low Deal Margin
Project Duration
| Phase |  |  | Weeks | Notes
| Inception Phase |  |  | 1 | Includes Internal Client Kickoff
| Definition Phase |  |  | 2 | Includes Requirements Workshop
| Build Phase |  |  | 6 | Includes Build, Design, Customer SO
| Deploy Phase |  |  | 6 | Includes User Acceptance and Cutover
| Close Phase |  |  | 1 | Includes Confirm Completion, Post Implementation Review and Project Close Out
|  | Total Project Length (Weeks) |  | 16
Project Settings
| Parameters |  |  |  | Options
| Operational Model |  |  |  | New Fixed Price Project
| Build Complexity |  |  |  | Standard Offering with Customization
| Number of Sites |  |  |  | <10
| Geographic Dispersion |  |  |  | Single Country - Single Site
| Solution Scope |  |  |  | 2-3 BUs
| Customer Experience |  |  |  | Good
Project Template
| Recommended |  |  | Standard
Override
Reason
Project Risk
| Recommended |  |  | 2.5%
Service Override
Service Override Reason
Governance Override
Governance Override Reason
Payment Milestones
Component |  |  | Amount Due ($) |  | Amount Due (%) | Deliverable | Internal Notes
Services |  |  | 54997.17 |  | 25% | on Contract signature
Services |  |  | 54997.17 |  | 25% | on Completion of definition
Services |  |  | 54997.17 |  | 25% | on Completion of build
Services |  |  | 54997.16 |  | 25% | on Acceptance of project completion
Service Change Request |  |  |  |  | 100% | as defined in Change Request
Accomodation, subsistence and travel |  |  | 0 |  | 100% | on Order

## Financials
| Cost w/o Risk | Risk | Cost + Risk | Margin | Sell Price | Margin % | Margin % w/o risk
Grand Total | 129579 | 3087.11 | 132666.11 | 87322.56 | 219988.67 | 39.69% | 41.1%
Grand Total Services | 98908 | 2472.71 | 101380.71 | 58509.55 | 159890.26 | 36.59% | 38.14%
Grand Total Governance | 24576 | 614.4 | 25190.4 | 14794.36 | 39984.76 | 37% | 38.54%
Grand Total Contractor Info | 6095 |  | 6095 | 14018.65 | 20113.65 | 69.7% | 69.7%
Grand Total Travel & Expense
Total Networking | 90122 | 2100.68 | 92222.68 | 64601.57 | 156824.25 | 41.19% | 42.53%
Services | 59451 | 1486.28 | 60937.28 | 35788.56 | 96725.84 | 37% | 38.54%
Governance | 24576 | 614.4 | 25190.4 | 14794.36 | 39984.76 | 37% | 38.54%
Contractor Info | 6095 |  | 6095 | 14018.65 | 20113.65 | 69.7% | 69.7%
Travel & Expense
Total Security | 39457 | 986.43 | 40443.43 | 22720.99 | 63164.42 | 35.97% | 37.53%
Services | 39457 | 986.43 | 40443.43 | 22720.99 | 63164.42 | 35.97% | 37.53%
Governance
Contractor Info
Travel & Expense

## Sub Contractor
Service Name | Activity/Phase | Business Unit | Vendor Name | Description | List Price | Discount | Total Cost | Margin Percent | Total Margin | Total Price | Notes
Camera & Sensor installation | 04 - Deploy | Networking | Staley | Physical installation of Meraki cameras and sensors | 6095 | 0% | 6095 | 69.7% | 14018.65 | 20113.65

## Governance
Business Unit | Activity/Phase | Outcome/Task | Role | Rate Type | Effort (hrs) | Quantity | Total Hours | Cost Rate | Total Cost | Notes
Networking | 00 - Project Governance | PM Time | Sr. Project Manager (L3) | Normal | 12 | 16 | 192 | 128 | 24576 | 8 Hours a week for duration of project

## Travel & Expenses
Business Unit | Activity/Phase | Description | Total Cost | Margin Percent | Total Price | Total Margin | Notes

## Capacity Report
Task Resource | Total Hours | Total Cost | Average Cost Rate
Associate Project Manager (L1) | 28 | 2296 | 82
Sr. Project Manager (L3) | 192 | 24576 | 128
TS Implementation Engineer (L1) | 80 | 5680 | 71
TS Implementation Engineer (L2) | 13 | 1482 | 114
TS Implementation Engineer (L3) | 355 | 51475 | 145
TS Implementation Engineer (L4) | 245 | 37975 | 155

## Internal Quote Report
RowType | LineNum | Manufacturer | MfrPartNum | Quantity | UOM | Description | CurrencyCode | ListPrice | Cost | UnitPrice | ItemType | SolutionType | InternalComments
1 | 10 | Dimension Data Global | DDPS-ProjectDeliveryServices | 1 | EA | Project Delivery Services FP | USD | 156824.25 | 92222.68 | 156824.25 | 3 | NI | IPA Version 20210716.1
1 | 20 | Dimension Data Global | DDPS-ProjectDeliveryServices | 1 | EA | Project Delivery Services FP | USD | 63164.42 | 40443.43 | 63164.42 | 3 | SE | IPA Version 20210716.1

## Detail Report
Service Name | Service Catalog | Business Unit | Activity/Phase | Outcome/Task | Role | Effort (hrs) | Quantity | Total Hours | Cost Rate | Total Cost (before risk) | Notes
Network - LAN | Network - LAN | Networking | 01 - Inception | Design requirements and feature workshop | TS Implementation Engineer (L3) | 16 | 1 | 16 | 145 | 2320 | Core / distribution/access design, L3 to access, VLAN mappings, closet mappings, routing architecture, etc
Network - LAN | Network - LAN | Networking | 02 - Definition | Detailed requirements gathering / high level network analysis | TS Implementation Engineer (L3) | 16 | 1 | 16 | 145 | 2320
Network - LAN | Network - LAN | Networking | 02 - Definition | Create Microdesign, Switch Configurations, diagrams, & test plan | TS Implementation Engineer (L3) | 32 | 1 | 32 | 145 | 4640
Network - LAN | Network - LAN | Networking | 03 - Build | Create Acceptance test plan | TS Implementation Engineer (L3) | 16 | 1 | 16 | 145 | 2320
Network - LAN | Network - LAN | Networking | 03 - Build | Unbox Catalyst Switches, inspect for damage, POST testing, update IOS (per Switch) | Associate Project Manager (L1) | 1 | 17 | 17 | 82 | 1394 | (97) 3400s (71) 3400 Expansion modules (22) 9300s/9500s
Network - LAN | Network - LAN | Networking | 03 - Build | Load configurations on Catalyst Switches, IOS upgrades, and captures sent to L3 for review (per Switch) | Associate Project Manager (L1) | 0.5 | 22 | 11 | 82 | 902
Network - LAN | Network - LAN | Networking | 03 - Build | Assist L2 engineer with installation and patching (per closet) | TS Implementation Engineer (L1) | 8 | 10 | 80 | 71 | 5680
Network - LAN | Network - LAN | Networking | 03 - Build | Execute Test and Acceptance plan (per closet) | TS Implementation Engineer (L3) | 2 | 10 | 20 | 145 | 2900
Network - LAN | Network - LAN | Networking | 03 - Build | Staging IE3400 Switches | TS Implementation Engineer (L3) | 37 | 1 | 37 | 145 | 5365
Network - LAN | Network - LAN | Networking | 04 - Deploy | Install Catalyst Switches in Rack, connect uplink cables and cutover (per closet) | TS Implementation Engineer (L3) | 4 | 10 | 40 | 145 | 5800
Network - LAN | Network - LAN | Networking | 04 - Deploy | Deploy IE3400 Switch | TS Implementation Engineer (L3) | 1 | 60 | 60 | 145 | 8700
Network - LAN | Network - LAN | Networking | 06 - KnowledgeTransfer | Training/Knowledge transfer | TS Implementation Engineer (L3) | 8 | 1 | 8 | 145 | 1160
Network - LAN | Network - LAN | Networking | 06 - KnowledgeTransfer | Create as-built documentation set | TS Implementation Engineer (L3) | 10 | 3 | 30 | 145 | 4350
Network - LAN | Network - LAN | Networking | 06 - KnowledgeTransfer | Post-Cutover Support | TS Implementation Engineer (L3) | 8 | 10 | 80 | 145 | 11600
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 02 - Definition | data gathering and analysis | TS Implementation Engineer (L4) | 16 | 1 | 16 | 155 | 2480 | FPR, Stealthwatch, Cybervision, Umbrella
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 02 - Definition | design workshop | TS Implementation Engineer (L4) | 16 | 1 | 16 | 155 | 2480 | FPR, Stealthwatch, Cybervision, Umbrella
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 03 - Build | develop detailed design document | TS Implementation Engineer (L4) | 16 | 1 | 16 | 155 | 2480
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 03 - Build | develop test plan | TS Implementation Engineer (L4) | 4 | 1 | 4 | 155 | 620
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 03 - Build | rack, stack, cable, install hw/sw | TS Implementation Engineer (L2) | 1 | 2 | 2 | 114 | 228
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 03 - Build | Stealthwatch Build and Deploy | TS Implementation Engineer (L4) | 40 | 1 | 40 | 155 | 6200 | Includes build-out of platform and configuration of solution
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 03 - Build | Firepower 2110 x2 Build and Deploy | TS Implementation Engineer (L4) | 40 | 1 | 40 | 155 | 6200 | Includes configuration of platform - Policies, NAT, VPN, routing, Etc.
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 03 - Build | Umbrella SIG Build and Deploy | TS Implementation Engineer (L4) | 40 | 1 | 40 | 155 | 6200 | Build-out of policy for proxy to Internet for IOT devices
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 03 - Build | Meraki MV Cameras and Sensors | TS Implementation Engineer (L2) | 0.5 | 22 | 11 | 114 | 1254 | 10 x MV Cameras and 10 x sensors for data closets
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 06 - KnowledgeTransfer | handover/knowledge transfer | TS Implementation Engineer (L4) | 8 | 1 | 8 | 155 | 1240
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 06 - KnowledgeTransfer | Create Documentation | TS Implementation Engineer (L4) | 10 | 3 | 30 | 155 | 4650
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 07 - Cutover | migration/cutover | TS Implementation Engineer (L4) | 16 | 1 | 16 | 155 | 2480
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 09 - Testing | failover testing | TS Implementation Engineer (L4) | 3 | 1 | 3 | 155 | 465
Security 4. Firewall/UTM Deployment | Security 4. Firewall/UTM Deployment | Security | 09 - Testing | next day support | TS Implementation Engineer (L4) | 8 | 2 | 16 | 155 | 2480
Governance | Governance | Networking | 00 - Project Governance | PM Time | Sr. Project Manager (L3) | 12 | 16 | 192 | 128 | 24576 | 8 Hours a week for duration of project